## ProjectSchedule
Southern Lee County Flood Protection Plan
AIM/Lee County Schedule
|  | Project Start: | 2018-11-01
|  | Display Week: | 1 |  |  | 2018-10-29 | [6 empty] | 2018-11-05 | [6 empty] | 2018-11-12 | [6 empty] | 2018-11-19 | [6 empty] | 2018-11-26 | [6 empty] | 2018-12-03 | [6 empty] | 2018-12-10 | [6 empty] | 2018-12-17 | [6 empty] | 2018-12-24 | [6 empty] | 2018-12-31 | [6 empty] | 2019-01-07 | [6 empty] | 2019-01-14 | [6 empty] | 2019-01-21 | [6 empty] | 2019-01-28 | [6 empty] | 2019-02-04 | [6 empty] | 2019-02-11 | [6 empty] | 2019-02-18 | [6 empty] | 2019-02-25 | [6 empty] | 2019-03-04 | [6 empty] | 2019-03-11 | [6 empty] | 2019-03-18 | [6 empty] | 2019-03-25 | [6 empty] | 2019-04-01 | [6 empty] | 2019-04-08 | [6 empty] | 2019-04-15 | [6 empty] | 2019-04-22 | [6 empty] | 2019-04-29 | [6 empty] | 2019-05-06 | [6 empty] | 2019-05-13 | [6 empty] | 2019-05-20 | [6 empty] | 2019-05-27 | [6 empty] | 2019-06-03 | [6 empty] | 2019-06-10 | [6 empty] | 2019-06-17 | [6 empty] | 2019-06-24 | [6 empty] | 2019-07-01 | [6 empty] | 2019-07-08 | [6 empty] | 2019-07-15 | [6 empty] | 2019-07-22 | [6 empty] | 2019-07-29 | [6 empty] | 2019-08-05 | [6 empty] | 2019-08-12 | [6 empty] | 2019-08-19 | [6 empty] | 2019-08-26 | [6 empty] | 2019-09-02 | [6 empty] | 2019-09-09 | [6 empty] | 2019-09-16 | [6 empty] | 2019-09-23 | [6 empty] | 2019-09-30 | [6 empty] | 2019-10-07 | [6 empty] | 2019-10-14 | [6 empty] | 2019-10-21 | [6 empty] | 2019-10-28 | [6 empty] | 2019-11-04
 | time axis 2018-10-29 to 2019-11-10
TASK | ASSIGNED TO | PROGRESS | START | END | DAYS | time axis 2018-10-29 to 2019-11-10
Task 1 Project Coordination |  |  | 2018-11-01 | 2019-10-31 | 365
Kickoff Meeting | AIM/County |  | 2018-11-05 | 2018-11-05 | 1
Monthly Progress Mtgs 1st Monday of month | AIM/County
Monthly Progress Repts w/Inv. By 15th of month | AIM
Task 2 Identification of Potential Flood Improvement Projects |  |  | 2018-11-12 | 2019-03-15 | 124
2.1 Peer Review of Phase II Rept/Other Key Docs | AIM |  | 2018-11-12 | 2019-01-04 | 54
Development of Draft Concept Projects | AIM |  | 2018-12-17 | 2019-01-15 | 30
2.2 Internal Workshop | AIM |  | 2019-01-15 | 2019-01-15 | 1
2.3 Summary Memo of Concept Projects - DRAFT | AIM |  | 2019-01-15 | 2019-02-08 | 25
AIM QA/QC | AIM |  | 2019-02-11 | 2019-02-15 | 5
County Review of Draft Summary Memo | County |  | 2019-02-18 | 2019-02-22 | 5
2.3 Finalize Summary Memo of Concept Projects | AIM |  | 2019-02-22 | 2019-03-08 | 15
AIM QA/QC | AIM |  | 2019-03-11 | 2019-03-15 | 5
Final Concept Projects Summary Memo | AIM |  | 2019-03-15 | 2019-03-15 | 1
Task 3 Regional Model Development |  |  | 2018-11-12 | 2019-04-01 | 141
3.1 Regional Model Initial Data Collection Summary Memorandum | AIM |  | 2018-11-12 | 2018-11-28 | 17
AIM QA/QC | AIM |  | 2018-11-28 | 2018-12-03 | 6
3.1 Regional Model Initial Data Collection Summary Memorandum | AIM |  | 2018-12-03 | 2018-12-03
3.2 Regional Model Development Summary Presentation | AIM |  | 2018-12-03 | 2019-01-03 | 32
AIM QA/QC | AIM |  | 2019-01-03 | 2019-01-07 | 5
3.2 Regional Model Development Summary Presentation | AIM |  | 2019-01-07 | 2019-01-07
3.3 Draft Existing Conditions Model Report | AIM |  | 2019-01-07 | 2019-03-01 | 54
AIM QA/QC | AIM |  | 2019-03-04 | 2019-03-08 | 5
County Review of Draft Report | County |  | 2019-03-11 | 2019-03-15 | 5
3.4 Final Existing Conditions Model Report | AIM |  | 2019-03-18 | 2019-03-22 | 5
AIM QA/QC | AIM |  | 2019-03-25 | 2019-04-01 | 8
3.4 Final Existing Conditions Model Report | AIM |  | 2019-04-01 | 2019-04-01 | 1
Task 4 Modeling |  |  | 2019-03-18 | 2019-07-15 | 120
Tasks 4.1 - 4.5 Project Screening with Regional Model | AIM |  | 2019-03-18 | 2019-05-17 | 61
AIM QA/QC | AIM |  | 2019-05-20 | 2019-05-24 | 5
Tasks 4.6-4.5 Draft Regional Project Evaluation Memorandum | AIM |  | 2019-05-20 | 2019-06-18 | 30
AIM QA/QC of Regl Model Summary Memo | AIM |  | 2019-06-19 | 2019-06-25 | 7
County Review of Regl Model Summary Memo | County |  | 2019-06-26 | 2019-07-02 | 7
Final Regl Model Summary Revisions | AIM |  | 2019-07-03 | 2019-07-10 | 8
AIM QA/QC | AIM |  | 2019-07-11 | 2019-07-15 | 5
Final Regl Model Summary | AIM |  | 2019-07-15 | 2019-07-15 | 1
Determination of 5 Local Model Projects | County |  | TBD | TBD | #VALUE!
Local Model Development | AIM |  | TBD | TBD | #VALUE!
AIM QA/QC of Local Model Summary Memo | AIM |  | TBD | TBD | #VALUE!
County Review of Local Model Summary Memo | County |  | TBD | TBD | #VALUE!
Final Local Model Summary Memo Revisions | AIM |  | TBD | TBD | #VALUE!
AIM QA/QC of Final Local Model Summary Memo | AIM |  | TBD | TBD | #VALUE!
Final Local Model Summary Memo | AIM |  | TBD | TBD | #VALUE!
Task 5 Surveying | AIM |  | 2019-02-22 | 2019-06-10 | 109
Task 6 Agency Coordination | AIM |  | 2018-11-08
First Meeting w/all agencies | AIM/County |  | 2018-11-08 | 2018-12-07 | 30
Follow Up Meetings | AIM/County |  | TBD | TBD | #VALUE!
Task 7 Project Evaluation Reports | AIM |  | 2019-07-16 | 2019-09-11 | 58
Draft Project Eval Reports | AIM |  | 2019-07-16 | 2019-08-14 | 30
AIM QA/QC | AIM |  | 2019-08-14 | 2019-08-21 | 8
County Review of Draft Proj Eval Reports | County |  | 2019-08-22 | 2019-08-28 | 7
Final Proj Eval Report Revisions | AIM |  | 2019-08-29 | 2019-09-06 | 9
AIM QA/QC | AIM |  | 2019-09-09 | 2019-09-12 | 4
Final Proj Eval Report | AIM |  | 2019-09-12 | 2019-09-12 | 1
Task 8 Priority Matrix |  |  | 2019-08-14 | 2019-10-04 | 52
Draft Priority Matrix | AIM |  | 2019-08-14 | 2019-09-12 | 30
AIM QA/QC | AIM |  | 2019-09-12 | 2019-09-16 | 5
County Review of Priority Matrix | County |  | 2019-09-17 | 2019-09-23 | 7
Final Priority Matrix Revisions | AIM |  | 2019-09-24 | 2019-09-30 | 7
AIM QA/QC | AIM |  | 2019-10-01 | 2019-10-04 | 4
Final Priority Matrix | AIM |  | 2019-10-04 | 2019-10-04 | 1
Task 9 Public Involvement |  |  | 2018-11-01 | 2019-10-31 | 365
Open Houses | AIM/County |  | TBD | TBD | #VALUE!
BOCC Presentation | AIM/County |  | TBD | TBD | #VALUE!
Task 10 Build Out Analysis |  |  | 2019-06-24 | 2019-09-20 | 89
Draft Build Out Analysis Memo | AIM |  | 2019-06-24 | 2019-08-23 | 61
AIM QA/QC | AIM |  | 2019-08-23 | 2019-08-30 | 8
County Review of Build Out Analysis Memo | County |  | 2019-08-30 | 2019-09-06 | 8
Final Build Out Analysis Revisions | AIM |  | 2019-09-09 | 2019-09-13 | 5
AIM QA/QC | AIM |  | 2019-09-16 | 2019-09-20 | 5
Final Build Out Analysis Memo | AIM |  | 2019-09-20 | 2019-09-20 | 1
Task 11 Basin Storage/Discharge Analysis | AIM |  | 2019-09-09 | 2019-10-25 | 47
Draft Basin Storage/Discharge Analysis Memo | AIM |  | 2019-09-09 | 2019-10-04 | 26
AIM QA/QC | AIM |  | 2019-10-04 | 2019-10-11 | 8
County Review of Storage/Discharge Memo | County |  | 2019-10-11 | 2019-10-18 | 8
Final Revisions of Storage/Discharge Memo | AIM |  | 2019-10-18 | 2019-10-22 | 5
AIM QA/QC | AIM |  | 2019-10-22 | 2019-10-25 | 4
Final Basin Storage/Dischg Anal. Memo | AIM |  | 2019-10-25 | 2019-10-25 | 1
Task 12 Summary Report |  |  | 2019-09-02 | 2019-10-31 | 60
Draft Summary Report | AIM |  | 2019-09-02 | 2019-10-07 | 36
AIM QA/QC | AIM |  | 2019-10-07 | 2019-10-11 | 5
County Review | County |  | 2019-10-14 | 2019-10-18 | 5
Final Summary Report Revisions | AIM |  | 2019-10-21 | 2019-10-25 | 5
AIM QA/QC | AIM |  | 2019-10-28 | 2019-10-31 | 4
Final Summary Report | AIM |  | 2019-10-31 | 2019-10-31 | 1
Insert new rows ABOVE this one
SIMPLE GANTT CHART by Vertex42.com |  |  |  | 2018-01-13
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
Note on H6: DAYS: This column calculates the duration of the task in calendar days. The duration includes both the Start and End dates.

## About
SIMPLE GANTT CHART by Vertex42.com
https://www.vertex42.com/ExcelTemplates/simple-gantt-chart.html
About This Template
This template provides a simple way to create a Gantt chart to help visualize and track your project. Simply enter your tasks and start and end dates - no formulas required. The bars in the Gantt chart represent the duration of the task and are displayed using conditional formatting. Insert new tasks by inserting new rows.
Additional Help
Click on the link below to visit vertex42.com and learn more about how to use this template, such as how to calculate days and work days, create task dependencies, change the colors of the bars, add a scroll bar to make it easier to change the display week, extend the date range displayed in the chart, etc.
How to Use the Simple Gantt Chart
More Project Management Templates
Visit Vertex42.com to download other project management templates, including different types of project schedules, Gantt charts, tasks lists, etc.
Project Management Templates
About Vertex42
Vertex42.com provides over 300 professionally designed spreadsheet templates for business, home, and education - most of which are free to download. Their collection includes a variety of calendars, planners, and schedules as well as personal finance spreadsheets for budgeting, debt reduction, and loan amortization.
Businesses will find invoices, time sheets, inventory trackers, financial statements, and project planning templates. Teachers and students will find resources such as class schedules, grade books, and attendance sheets. Organize your family life with meal planners, checklists, and exercise logs. Each template is thoroughly researched, refined, and improved over time through feedback from thousands of users.